## Sheet1
Approx. dates	SPRINT 1		Approx. dates	SPRINT 3		Approx. dates	SPRINT 5
02 / 25	MUST		03 / 12	MUST		03 / 28	MUST
	Sorting unit testing			Decide on specific parts of iot pen test methodology to be implemented			export methodology as serialized data
	global app config.ini file and settings			List of tools for iot pen testing to be included			methodology loading, saving, creation
	define yaml files structure for interface files			SHOULD			threat model data transfer to pen tools
	SHOULD			nested flags support for interfaces			threat object ranking according to DREAD
	parsing interfaces from yaml files			compose yaml files for iot pen testing tools			SHOULD
	interface Model structure			COULD			overall gui update to include status bar etc
	COULD			fix up interface gui			separate pen tool output displays
	first gui try			interface flag separation by labels			COULD
03 / 05	WON’T		03 / 19	WON’T			clear method cache
						04 / 05	WON’T
Approx. dates	SPRINT 2		Approx. dates	SPRINT 4			export method as html
03 / 06	MUST		03 / 20	MUST
	interface gui generation			compose yaml files for iot pen testing tools
	command generation from gui and execution			methodology data structures
	SHOULD			methodology dumb gui
	multithreaded command execution			main gui integrate methodology gui
	command run termination			SHOULD
	COULD			threat object ranking according to DREAD
	interface tab structure			connect methodology model and gui
	WON’T			COULD
	proper formatting for interfacae gui			exporting methodology object
03 / 12	Proper styling for interface gui			methodology loading, saving, creation
			03 / 27	WON’T